## Baseline_Comparison
ID | Name | Duration | Start_Date | Finish_Date | Scheduled_Work | Cost | Baseline_Estimated_Duration | Baseline_Start | Baseline_Finish | Baseline_Work | Baseline_Cost | Duration_Variance | Work_Variance | Cost_Variance
1 | Project Management Activities | 14.5 hrs | April 19, 2022 8:00 AM | June 24, 2022 10:00 AM | 21h | 657.5 | 386h | April 19, 2022 8:00 AM | June 24, 2022 10:00 AM | 21h | 657.5 | 0h | 0h | 0
2 | Research Business Case | 1 hr | April 19, 2022 8:00 AM | April 19, 2022 9:00 AM | 1h | 30 | 1h | April 19, 2022 8:00 AM | April 19, 2022 9:00 AM | 1h | 30 | 0h | 0h | 0
3 | Create Charter | 4 hrs | April 22, 2022 8:00 AM | April 22, 2022 12:00 PM | 4h | 120 | 4h | April 22, 2022 8:00 AM | April 22, 2022 12:00 PM | 4h | 120 | 0h | 0h | 0
4 | Ratify Charter | 1 hr | April 25, 2022 8:00 AM | April 25, 2022 9:00 AM | 3h | 95 | 1h | April 25, 2022 8:00 AM | April 25, 2022 9:00 AM | 3h | 95 | 0h | 0h | 0
5 | Create WBS | 3 hrs | April 26, 2022 8:00 AM | April 26, 2022 11:00 AM | 3h | 90 | 3h | April 26, 2022 8:00 AM | April 26, 2022 11:00 AM | 3h | 90 | 0h | 0h | 0
6 | Assign Resources & Schedule | 2 hrs | April 27, 2022 8:00 AM | April 27, 2022 10:00 AM | 2h | 60 | 2h | April 27, 2022 8:00 AM | April 27, 2022 10:00 AM | 2h | 60 | 0h | 0h | 0
7 | Stakeholder Check-in/Comm. Plan Matrix | 1 hr | April 29, 2022 9:00 AM | April 29, 2022 10:00 AM | 2h | 65 | 1h | April 29, 2022 9:00 AM | April 29, 2022 10:00 AM | 2h | 65 | 0h | 0h | 0
8 | Introductory Letter | 0.5 hrs | May 2, 2022 8:00 AM | May 2, 2022 8:30 AM | 1h | 32.5 | 0.5h | May 2, 2022 8:00 AM | May 2, 2022 8:30 AM | 1h | 32.5 | 0h | 0h | 0
9 | Progress Report | 1 hr | May 20, 2022 8:00 AM | May 20, 2022 9:00 AM | 1h | 30 | 1h | May 20, 2022 8:00 AM | May 20, 2022 9:00 AM | 1h | 30 | 0h | 0h | 0
10 | Final Report | 1 hr | June 24, 2022 9:00 AM | June 24, 2022 10:00 AM | 4h | 135 | 1h | June 24, 2022 9:00 AM | June 24, 2022 10:00 AM | 4h | 135 | 0h | 0h | 0
12 | Interview PSS DPF Family Navigator Services | 49.5 hrs | May 3, 2022 8:00 AM | May 11, 2022 9:30 AM | 6h | 150 | 9h | May 3, 2022 8:00 AM | May 4, 2022 9:00 AM | 8h | 200 | 40.5h | -2h | -50
13 | Seattle PSS | 0.5 hrs | May 11, 2022 9:00 AM | May 11, 2022 9:30 AM | 1h | 25 | 1h | May 3, 2022 8:00 AM | May 3, 2022 9:00 AM | 2h | 50 | -0.5h | -1h | -25
14 | Kent PSS | 1 hr | May 3, 2022 8:00 AM | May 3, 2022 9:00 AM | 2h | 50 | 1h | May 3, 2022 8:00 AM | May 3, 2022 9:00 AM | 2h | 50 | 0h | 0h | 0
15 | Olympia PSS | 1 hr | May 4, 2022 8:00 AM | May 4, 2022 9:00 AM | 2h | 50 | 1h | May 4, 2022 8:00 AM | May 4, 2022 9:00 AM | 2h | 50 | 0h | 0h | 0
16 | Spokane PSS | 0.5 hrs | May 4, 2022 8:00 AM | May 4, 2022 8:30 AM | 1h | 25 | 1h | May 4, 2022 8:00 AM | May 4, 2022 9:00 AM | 2h | 50 | -0.5h | -1h | -25
17 | Document DPF | 4.5 hrs | May 12, 2022 9:00 AM | May 12, 2022 2:30 PM | 4.5h | 135 | 3h | May 5, 2022 8:00 AM | May 5, 2022 11:00 AM | 3h | 90 | 1.5h | 1.5h | 45
18 | Evaluate Prototype | 1 hr | May 6, 2022 9:00 AM | May 6, 2022 10:00 AM | 2h | 60 | 0.5h | May 6, 2022 8:00 AM | May 6, 2022 8:30 AM | 1h | 30 | 0.5h | 1h | 30
19 | Validate Doc DFP w/ PSS Group | 2 hrs | May 12, 2022 9:00 AM | May 12, 2022 11:00 AM | 6h | 160 | 1h | May 6, 2022 8:00 AM | May 6, 2022 9:00 AM | 3h | 80 | 1h | 3h | 80
20 | Stakeholder Check-in | 1 hr | May 6, 2022 9:00 AM | May 6, 2022 10:00 AM | 2h | 65 | 1h | May 6, 2022 9:00 AM | May 6, 2022 10:00 AM | 2h | 65 | 0h | 0h | 0
21 | Deliver Analysis, Recommendations & Implementation Plan | 0.5 hrs | May 9, 2022 9:00 AM | May 9, 2022 9:30 AM | 1.5h | 47.5 | 0.5h | May 9, 2022 9:00 AM | May 9, 2022 9:30 AM | 1.5h | 47.5 | 0h | 0h | 0
22 | Approve Prototype | 0.5 hrs | May 10, 2022 9:00 AM | May 10, 2022 9:30 AM | 1.5h | 47.5 | 0.5h | May 9, 2022 9:00 AM | May 9, 2022 9:30 AM | 1.5h | 47.5 | 0h | 0h | 0
23 | Manage Plan, Schedule & Stakeholders | 3 hrs | May 9, 2022 9:00 AM | May 9, 2022 12:00 PM | 3h | 90 | 1h | May 9, 2022 9:00 AM | May 9, 2022 10:00 AM | 1h | 30 | 2h | 2h | 60
25 | Interview PSS DPF Volunteer Services | 9 hrs | May 10, 2022 9:00 AM | May 11, 2022 10:00 AM | 8h | 200 | 9h | May 10, 2022 9:00 AM | May 11, 2022 10:00 AM | 8h | 200 | 0h | 0h | 0
26 | Seattle PSS | 1 hr | May 11, 2022 9:00 AM | May 11, 2022 10:00 AM | 2h | 50 | 1h | May 10, 2022 9:00 AM | May 10, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
27 | Kent PSS | 1 hr | May 10, 2022 9:00 AM | May 10, 2022 10:00 AM | 2h | 50 | 1h | May 10, 2022 9:00 AM | May 10, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
28 | Olympia PSS | 1 hr | May 10, 2022 9:00 AM | May 10, 2022 10:00 AM | 2h | 50 | 1h | May 11, 2022 9:00 AM | May 11, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
29 | Spokane PSS | 1 hr | May 11, 2022 9:00 AM | May 11, 2022 10:00 AM | 2h | 50 | 1h | May 11, 2022 9:00 AM | May 11, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
30 | Document DPF | 6.5 hrs | May 18, 2022 9:00 AM | May 18, 2022 4:30 PM | 6.5h | 195 | 3h | May 12, 2022 9:00 AM | May 12, 2022 12:00 PM | 3h | 90 | 3.5h | 3.5h | 105
31 | Stakeholder Check-in | 1 hr | May 18, 2022 9:00 AM | May 18, 2022 10:00 AM | 1h | 35 | 1h | May 13, 2022 9:00 AM | May 13, 2022 10:00 AM | 1h | 35 | 0h | 0h | 0
32 | Seek Team Feedback | 1 hr | May 17, 2022 9:00 AM | May 17, 2022 10:00 AM | 3h | 95 | 1h | May 17, 2022 9:00 AM | May 17, 2022 10:00 AM | 3h | 95 | 0h | 0h | 0
33 | Validate Doc DFP w/ PSS Group | 1 hr | May 18, 2022 9:00 AM | May 18, 2022 10:00 AM | 2h | 50 | 1h | May 16, 2022 9:00 AM | May 16, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
34 | Deliver Analysis, Recommendations & Implementation Plan | 1 hr | May 24, 2022 9:00 AM | May 24, 2022 10:00 AM | 3h | 95 | 1h | May 17, 2022 9:00 AM | May 17, 2022 10:00 AM | 3h | 95 | 0h | 0h | 0
36 | Interview PSS DPF Supportive Housing Service | 9 hrs | May 16, 2022 9:00 AM | May 17, 2022 10:00 AM | 8h | 200 | 9h | May 17, 2022 9:00 AM | May 18, 2022 10:00 AM | 8h | 200 | 0h | 0h | 0
37 | Seattle PSS | 1 hr | May 16, 2022 9:00 AM | May 16, 2022 10:00 AM | 2h | 50 | 1h | May 17, 2022 9:00 AM | May 17, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
38 | Kent PSS | 1 hr | May 17, 2022 9:00 AM | May 17, 2022 10:00 AM | 2h | 50 | 1h | May 17, 2022 9:00 AM | May 17, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
39 | Olympia PSS | 1 hr | May 16, 2022 9:00 AM | May 16, 2022 10:00 AM | 2h | 50 | 1h | May 18, 2022 9:00 AM | May 18, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
40 | Spokane PSS | 1 hr | May 16, 2022 9:00 AM | May 16, 2022 10:00 AM | 2h | 50 | 1h | May 18, 2022 9:00 AM | May 18, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
41 | Document DPF | 5 hrs | May 26, 2022 9:00 AM | May 26, 2022 3:00 PM | 5h | 150 | 2h | May 19, 2022 9:00 AM | May 19, 2022 11:00 AM | 2h | 60 | 3h | 3h | 90
42 | Stakeholder Check-in | 1 hr | May 25, 2022 9:00 AM | May 25, 2022 10:00 AM | 2h | 65 | 1h | May 20, 2022 9:00 AM | May 20, 2022 10:00 AM | 2h | 65 | 0h | 0h | 0
43 | Seek Team Feedback | 0.5 hrs | May 24, 2022 9:00 AM | May 24, 2022 9:30 AM | 1.5h | 47.5 | 1h | May 24, 2022 9:00 AM | May 24, 2022 10:00 AM | 3h | 95 | -0.5h | -1.5h | -47.5
44 | Validate Doc DFP w/ PSS Group | 1 hr | May 27, 2022 9:00 AM | May 27, 2022 10:00 AM | 2h | 50 | 1h | May 20, 2022 9:00 AM | May 20, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
45 | Deliver Analysis, Recommendations & Implementation Plan | 0.5 hrs | May 31, 2022 9:00 AM | May 31, 2022 9:30 AM | 1.5h | 47.5 | 0.5h | May 23, 2022 9:00 AM | May 23, 2022 9:30 AM | 1.5h | 47.5 | 0h | 0h | 0
46 | Manage Plan, Schedule & Stakeholders | 3 hrs | May 24, 2022 9:00 AM | May 24, 2022 12:00 PM | 3h | 90 | 1h | May 23, 2022 9:00 AM | May 23, 2022 10:00 AM | 1h | 30 | 2h | 2h | 60
48 | Interview PSS DPF Supportive Employment Services | 25 hrs | May 23, 2022 9:00 AM | May 26, 2022 10:00 AM | 8h | 200 | 9h | May 24, 2022 9:00 AM | May 25, 2022 10:00 AM | 8h | 200 | 16h | 0h | 0
49 | Seattle PSS | 1 hr | May 26, 2022 9:00 AM | May 26, 2022 10:00 AM | 2h | 50 | 1h | May 24, 2022 9:00 AM | May 24, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
50 | Kent PSS | 1 hr | May 25, 2022 9:00 AM | May 25, 2022 10:00 AM | 2h | 50 | 1h | May 24, 2022 9:00 AM | May 24, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
51 | Olympia PSS | 1 hr | May 25, 2022 9:00 AM | May 25, 2022 10:00 AM | 2h | 50 | 1h | May 25, 2022 9:00 AM | May 25, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
52 | Spokane PSS | 1 hr | May 23, 2022 9:00 AM | May 23, 2022 10:00 AM | 2h | 50 | 1h | May 25, 2022 9:00 AM | May 25, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
53 | Document DPF | 2.5 hrs | May 30, 2022 9:00 AM | May 30, 2022 11:30 AM | 2.5h | 75 | 2h | May 26, 2022 9:00 AM | May 26, 2022 11:00 AM | 2h | 60 | 0.5h | 0.5h | 15
54 | Seek Team Feedback | 1 hr | May 31, 2022 9:00 AM | May 31, 2022 10:00 AM | 3h | 95 | 1h | May 31, 2022 9:00 AM | May 31, 2022 10:00 AM | 3h | 95 | 0h | 0h | 0
55 | Validate Doc DFP w/ PSS Group | 1 hr | May 31, 2022 9:00 AM | May 31, 2022 10:00 AM | 2h | 50 | 1h | May 27, 2022 9:00 AM | May 27, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
56 | Stakeholder Check-in | 1 hr | May 27, 2022 9:00 AM | May 27, 2022 10:00 AM | 2h | 65 | 1h | May 27, 2022 9:00 AM | May 27, 2022 10:00 AM | 2h | 65 | 0h | 0h | 0
57 | Deliver Analysis, Recommendations & Implementation Plan | 0.5 hrs | May 30, 2022 9:00 AM | May 30, 2022 9:30 AM | 1.5h | 47.5 | 0.5h | May 30, 2022 9:00 AM | May 30, 2022 9:30 AM | 1.5h | 47.5 | 0h | 0h | 0
59 | Interview PSS DPF Group Services | 17 hrs | May 30, 2022 9:00 AM | June 1, 2022 10:00 AM | 8h | 200 | 9h | May 30, 2022 9:00 AM | May 31, 2022 10:00 AM | 8h | 200 | 8h | 0h | 0
60 | Seattle PSS | 1 hr | May 31, 2022 9:00 AM | May 31, 2022 10:00 AM | 2h | 50 | 1h | May 30, 2022 9:00 AM | May 30, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
61 | Kent PSS | 1 hr | May 30, 2022 9:00 AM | May 30, 2022 10:00 AM | 2h | 50 | 1h | May 30, 2022 9:00 AM | May 30, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
62 | Olympia PSS | 1 hr | May 31, 2022 9:00 AM | May 31, 2022 10:00 AM | 2h | 50 | 1h | May 31, 2022 9:00 AM | May 31, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
63 | Spokane PSS | 1 hr | June 1, 2022 9:00 AM | June 1, 2022 10:00 AM | 2h | 50 | 1h | May 31, 2022 9:00 AM | May 31, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
64 | Document DPF | 3 hrs | June 13, 2022 9:00 AM | June 13, 2022 12:00 PM | 3h | 90 | 2h | May 31, 2022 9:00 AM | May 31, 2022 11:00 AM | 2h | 60 | 1h | 1h | 30
65 | Validate Doc DFP w/ PSS Group | 1 hr | June 1, 2022 9:00 AM | June 1, 2022 10:00 AM | 2h | 50 | 1h | June 1, 2022 9:00 AM | June 1, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
66 | Deliver Analysis, Recommendations & Implementation Plan | 1 hr | June 2, 2022 9:00 AM | June 2, 2022 10:00 AM | 2h | 60 | 1h | June 2, 2022 9:00 AM | June 2, 2022 10:00 AM | 2h | 60 | 0h | 0h | 0
68 | Interview PSS DPF Peer Coaching Services | 41 hrs | June 1, 2022 9:00 AM | June 8, 2022 10:00 AM | 10h | 265 | 9h | June 2, 2022 9:00 AM | June 3, 2022 10:00 AM | 10h | 265 | 32h | 0h | 0
69 | Seattle PSS | 1 hr | June 1, 2022 9:00 AM | June 1, 2022 10:00 AM | 2h | 50 | 1h | June 2, 2022 9:00 AM | June 2, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
70 | Kent PSS | 1 hr | June 1, 2022 9:00 AM | June 1, 2022 10:00 AM | 2h | 50 | 1h | June 2, 2022 9:00 AM | June 2, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
71 | Olympia PSS | 1 hr | June 8, 2022 9:00 AM | June 8, 2022 10:00 AM | 2h | 50 | 1h | June 3, 2022 9:00 AM | June 3, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
72 | Spokane PSS | 1 hr | June 1, 2022 9:00 AM | June 1, 2022 10:00 AM | 2h | 50 | 1h | June 3, 2022 9:00 AM | June 3, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
73 | Stakeholder Check-in | 1 hr | June 3, 2022 9:00 AM | June 3, 2022 10:00 AM | 2h | 65 | 1h | June 3, 2022 9:00 AM | June 3, 2022 10:00 AM | 2h | 65 | 0h | 0h | 0
74 | Document DPF | 5 hrs | June 14, 2022 9:00 AM | June 14, 2022 3:00 PM | 5h | 150 | 2h | June 6, 2022 9:00 AM | June 6, 2022 11:00 AM | 2h | 60 | 3h | 3h | 90
75 | Seek Team Feedback | 1 hr | June 7, 2022 9:00 AM | June 7, 2022 10:00 AM | 3h | 95 | 1h | June 7, 2022 9:00 AM | June 7, 2022 10:00 AM | 3h | 95 | 0h | 0h | 0
76 | Validate Doc DFP w/ PSS Group | 1 hr | June 7, 2022 9:00 AM | June 7, 2022 10:00 AM | 2h | 50 | 1h | June 7, 2022 9:00 AM | June 7, 2022 10:00 AM | 2h | 50 | 0h | 0h | 0
77 | Deliver Analysis, Recommendations & Implementation Plan | 0.5 hrs | June 7, 2022 9:00 AM | June 7, 2022 9:30 AM | 1.5h | 47.5 | 0.5h | June 7, 2022 9:00 AM | June 7, 2022 9:30 AM | 1.5h | 47.5 | 0h | 0h | 0
78 | Manage Plan, Schedule & Stakeholders | 3 hrs | June 7, 2022 9:00 AM | June 7, 2022 12:00 PM | 3h | 90 | 1h | June 7, 2022 9:00 AM | June 7, 2022 10:00 AM | 1h | 30 | 2h | 2h | 60
99 | Collect Lessons Learned | 1 hr | June 24, 2022 8:00 AM | June 24, 2022 9:00 AM | 3h | 95 | 1h | June 24, 2022 8:00 AM | June 24, 2022 9:00 AM | 3h | 95 | 0h | 0h | 0
100 | Debrief Team | 1 hr | June 24, 2022 8:00 AM | June 24, 2022 9:00 AM | 3h | 95 | 1h | June 24, 2022 8:00 AM | June 24, 2022 9:00 AM | 3h | 95 | 0h | 0h | 0
101 | Thank Team and Adjourne | 1 hr | June 24, 2022 8:00 AM | June 24, 2022 9:00 AM | 5h | 155 | 1h | June 24, 2022 8:00 AM | June 24, 2022 9:00 AM | 5h | 155 | 0h | 0h | 0
| Totals |  |  |  |  | 6580 |  |  |  |  | 6062.5 |  |  | 517.5